PLAN:

What problem of practice will be addressed?

Out-of-school time activities can be better coordinated with SEL strategies implemented during the regular school day.

Continuous improvement aim: What is hoped to be achieved through this PDSA cycle?

Integrate SEL strategies that are implemented throughout the school day with out of school time activities.

Innovation to be tested: What change will be put into practice to achieve the aim?

Out-of-school time staff will learn about SEL strategies implemented during the school day and incorporate these strategies into out-of-school time.

Describe who will be implementing the innovation:

Out-of-school time staff

How long will the innovation be implemented before moving to the next step?

One month

What data source(s) will be used to determine extent to which aim is achieved?

Lesson plans from out of school time programs will include SEL strategies that align with SEL strategies implemented during the regular school day.

Based on the identified data sources, what metrics would be an indicator that the innovation is successful?

50% of out-of-school time lesson plans align with SEL strategies implemented during the regular school day.

DO:

What are high level observations from implementing the innovation? "To what extent did everything go as planned?"

Difficulties arose due to the different requirements between out-of-school time lesson plans and those used during the regular school day.

STUDY:

Team to utilize ATLAS Looking at Data Protocol to guide data inquiry discussions. Please summarize any Implications for Practice that the team generated through use of the ATLAS Looking at Data Protocol here.

75% of out-of-school time staff were able to align lesson plans with those that were developed by instructional staff.

ACT:

Team to utilize ATLAS Looking at Data Protocol to guide data inquiry discussions. Please summarize any Next Steps that the team generated through use of the ATLAS Looking at Data Protocol here.

Out-of-school time staff and instructional staff will continue to meet to coordinate SEL strategies implemented during the regular school day with those implemented after school.